## Project
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
User Story 1 | 5
Set up environment |  | Darrin | Done | 1 | 1: 0.75; 2: 0.5
Create Character |  | Darrin | Done | 0.5 | 1: 0; 2: 0.5
Allow it to move |  | Darrin | Done | 1 | 1: 0; 2: 1
User Story 2 | 3
Create code window |  | Ekaterina | Done | 0.5
Create animation window |  | Ekaterina | Done | 0.5
Create base page for animation and code window |  | Ekaterina | Done | 1
User Story 3 | 1
Landing page |  | Joseph | Done | 0.5 | 1: 0.5
Main menu |  | Joseph | Done | 1 | 2: 0.5
User Story 4 | 5
Create drag and drop method |  | Ekaterina | In Progress | 3 | 4: 2; 5: 1
User Story 5 | 1
Save page |  | Claudia and Loic | Done | 0.5 | 3: 0.5; 4: 0.5
Save method |  | Claudia | Done | 2 | 5: 0.75; 6: 0.75
User Story 6 | 3
Access/Load method |  | Claudia and Loic | In progress | 1 | 7: 0.5
User Story 7 | 5
Set up Travis |  | Emerald and Phuong-Thao | In progress | 15 | 2: 1; 3: 2.5; 5: 1; 8: 2; 9: 4
User Story 8 | 2
If Method |  |  | To be started | 1
User Story 9 | 2
Loop method |  |  | To be started | 1
User Story 10 | 0.5
Level Menu |  |  | To be started | 1
User Story 11 | 2
Jump method |  |  | To be started | 1
User Story 12 | 2
Attack/Break method |  |  | To be started | 1
User Story 13 | 5
View Progress Report |  |  | To be started | 5
User Story 14
Create different avatars | 1 |  | To be started | 1
Select an avatar | 1 |  | To be started | 1
User Story 15
Maximize Camera Run
Non-User Story Tasks
Story 1
Scrum Tools | 3 | Emerald and Phuong-Thao | Done | 3 | bar: 1 to 2; 6
Story 2
Testing | 3 | Everyone | To be started | 8
Story 3
Merging | 5 |  | To be started | 10
Total | 49.5 | 0 | 0 | 60.5 | 2.25 | 4.5 | 3 | 2.5 | 2.75 | 1.75 | 0.5 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Time |  |  |  | 60.5 | 1: 58.25; 2: 53.75; 3: 50.75; 4: 48.25; 5: 45.5; 6: 43.75; 7: 43.25; 8: 41.25; 9: 37.25; 10: 37.25
Points Total (day) |  |  |  |  | 1: 3; 2: 6; 6: 4; 7: 3
Points remaining |  |  |  |  | 46.5 | 40.5 | 40.5 | 40.5 | 40.5 | 36.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
Ideal burndown (day) |  |  |  | 1.5125 | 1.5125 | 3.025 | 4.5375 | 6.05 | 7.5625 | 9.075 | 10.5875 | 12.1 | 13.6125 | 15.125 | 16.6375 | 18.15 | 19.6625 | 21.175 | 22.6875 | 24.2 | 25.7125 | 27.225 | 28.7375 | 30.25 | 31.7625 | 33.275 | 34.7875 | 36.3 | 37.8125 | 39.325 | 40.8375 | 42.35 | 43.8625 | 45.375 | 46.8875 | 48.4 | 49.9125 | 51.425 | 52.9375 | 54.45 | 55.9625 | 57.475 | 58.9875 | 60.5
Ideal burndown remaining |  |  |  |  | 58.9875 | 57.475 | 55.9625 | 54.45 | 52.9375 | 51.425 | 49.9125 | 48.4 | 46.8875 | 45.375 | 43.8625 | 42.35 | 40.8375 | 39.325 | 37.8125 | 36.3 | 34.7875 | 33.275 | 31.7625 | 30.25 | 28.7375 | 27.225 | 25.7125 | 24.2 | 22.6875 | 21.175 | 19.6625 | 18.15 | 16.6375 | 15.125 | 13.6125 | 12.1 | 10.5875 | 9.075 | 7.5625 | 6.05 | 4.5375 | 3.025 | 1.5125 | 0

## Sprint 2
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
User Story 1 | 1
Set up environment |  | Darrin | Done | 1 | 1: 0.75; 2: 0.5
Create Character |  | Darrin | Done | 0.5 | 1: 0; 2: 0.5
Allow it to move |  | Darrin | Done | 1 | 1: 0; 2: 1
User Story 2 | 3
Create code window |  | Ekaterina | Done | 0.5
Create animation window |  | Ekaterina | Done | 0.5
Create base page for animation and code window |  | Ekaterina | Done | 1
User Story 3 | 1
Landing page |  | Joseph | Done | 0.5 | 1: 0.5
Main menu |  | Joseph | Done | 1 | 2: 0.5
User Story 4 | 5
Create drag and drop method |  | Ekaterina | Done | 3 | 4: 2; 5: 1
User Story 5 | 1
Save page |  | Claudia and Loic | Done | 0.5 | 3: 0.5; 4: 0.5
Save method |  | Claudia | Done | 2 | 5: 0.75; 6: 0.75
User Story 6 | 3
Access/Load method |  | Claudia and Loic | In progress | 1 | 7: 0.5
User Story 7 | 5
Set up Travis |  | Emerald and Phuong-Thao | In progress | 10 | 2: 1; 3: 2.5; 5: 1; 8: 2; 9: 4
Non-funtional Tasks
Scrum Tools | 3 | Emerald and Phuong-Thao | Done | 3 | bar: 1 to 10
Total | 22 |  |  | 25.5 | 2.25 | 4.5 | 3 | 2.5 | 2.75 | 1.75 | 0.5 | 2 | 4 | 0
Remaining Time |  |  |  | 25.5 | 23.25 | 18.75 | 15.75 | 13.25 | 10.5 | 8.75 | 8.25 | 6.25 | 2.25 | 2.25
Points Total (day) |  |  |  |  | 1: 6; 5: 5; 6: 3
Points remaining |  |  |  |  | 16 | 16 | 16 | 16 | 11 | 8 | 8 | 8 | 8 | 8
Ideal burndown (day) |  |  |  | 2.55 | 2.55 | 5.1 | 7.65 | 10.2 | 12.75 | 15.3 | 17.85 | 20.4 | 22.95 | 25.5
Ideal burndown remaining |  |  |  |  | 22.95 | 20.4 | 17.85 | 15.3 | 12.75 | 10.2 | 7.65 | 5.1 | 2.55 | 0