## Sprint 4
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Non-funtional Tasks
Requirement 1 | 3 |  |  | 6
Create Unit tests |  | Joseph & Loic | Done |  | 5: 1; 7: 2; 8: 3; 9: 1
Requirement 2 | 3 |  |  | 4
Acceptance Test |  | Phuong-Thao | Done |  | 1: 2; 4: 1; 7: 1; 9: 2
Requirement 3 | 0 |  |  | 4
Continuous Testing |  | Ekaterina, Emerald & Phuong-Thao |  |  | 6: 1.5
Requirement 4 | 5 |  |  | 7
Replacement of male avatar when female avatar is selected |  | Darrin | Done |  | 4: 2; 7: 4; 9: 1
Requirement 5 | 5 |  |  | 10
Refactor and fix code |  | Adam, Loic, Claudia, Joseph, Darrin | Done |  | 5: 2; 7: 5; 8: 5
Total | 16 |  |  | 31 | 2 | 0 | 0 | 3 | 3 | 1.5 | 12 | 8 | 4 | 0
Remaining Time |  |  |  |  | 29 | 29 | 29 | 26 | 23 | 21.5 | 9.5 | 1.5 | -2.5 | -2.5
Points Total (day) |  |  |  |  | 8: 5; 9: 11
Points remaining |  |  |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 11 | 0 | 0
Ideal burndown (day) |  |  |  | 1.6 | 1.6 | 3.2 | 4.8 | 6.4 | 8 | 9.6 | 11.2 | 12.8 | 14.4 | 16
Ideal burndown remaining |  |  |  |  | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0