## Sheet1
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
User Story 1 | 2
Save my progress on completed levels automatically |  | Claudia | Done | 2 | bar: 6 to 7
User Story 2 | 5
Move Left function |  | Phuong-Thao |  | 2.5 | 5: 2; 9: 1
Move Right function |  | Darrin | Done | 2.5 | 3: 2
Move Forward function |  | Darrin | Done | 2.5
Move Backward Function |  | Phuong-Thao | Done | 1.5 | 1: 2
Run Code Function |  | Darrin | Done | 3 | 4: 4
Clear Function |  | Darrin | Done | 3 | 6: 2
User Story 3 | 1
Create buttons to save and load file |  | Loic and Claudia | Done | 1.5 | bar: 5
User Story 4 | 3
TA view - display the number of students that have completed each level |  | Claudia | Done | 1.5 | bar: 7
User Story 5 | 2
See progress of one specific user |  | Loic | Done | 1.5 | bar: 7
User Story 6 | 3
User can Drag and Drop the blocks |  | Ekaterina | Done | 4 | 3: 1; 5: 1; 7: 1.5
User Story 7 | 5
Create a IF statement function |  | Adam |  | 2.5 | 9: 2; 10: 1
Create a WHILE statement function |  | Adam | Done | 2.5 | 7: 2
User Story 8 | 1
Create a level select page |  | Joseph | Done | 2 | bar: 4; 6
User Story 9 | 2
Container UI for the code Bocks |  | Adam | Done | 5 | 3: 2; 5: 2; 7: 2; 8: 5
Non-funtional Tasks
User Story 9 | 5
Work on additional CI |  | Emerald and Phuong-Thao | Doe | 4 | 4: 2; 6: 2; 9: 1
User Story 10 | 1
Create a link between the different pages |  | Joseph | Done | 1.5 | bar: 8
User Story 11 | 2
UML diagrams |  | Adam & Claudia | Done | 1.5 | 3: 0.5; 6: 0.5; 9: 0.5
Total | 32 |  |  | 44.5 | 2 | 0 | 5.5 | 7 | 6 | 6.5 | 8.5 | 6 | 4.5 | 1
Remaining Time |  |  |  | 44.5 | 42.5 | 42.5 | 37 | 30 | 24 | 17.5 | 9 | 3 | -1.5 | -2.5
Points Total (day) |  |  |  |  | 5: 1; 7: 10; 8: 2; 9: 9; 10: 5
Points remaining |  |  |  | 32 | 32 | 32 | 32 | 32 | 31 | 31 | 21 | 19 | 10 | 5
Ideal burndown (day) |  |  | 4.45 | 4.5 | 4.45 | 8.9 | 13.35 | 17.8 | 22.25 | 26.7 | 31.15 | 35.6 | 40.05 | 44.5
Ideal burndown remaining |  |  |  |  | 40.05 | 35.6 | 31.15 | 26.7 | 22.25 | 17.8 | 13.35 | 8.9 | 4.45 | 0