## Sprint 4
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
User Story 1 | 2 |  |  | 1
Option to select avatar |  | Loic | Done | bar: 2
User Story 2 | 2 |  |  | 1.5
Learn Drag and Drop |  | Ekaterina | Done | bar: 2
Create a destination point for level 1 |  | Ekaterina | Done | bar: 2
User Story 3 | 2 |  |  | 1.5
Create a destination point for level 2 |  | Ekaterina | Done |  | 3: 0.5
User Story 4 | 2 |  |  | 1.5
Create a destination point for level 3 |  | Ekaterina | Done |  | 8: 0.5
Create a pathway to limit the path option for level 3 |  | Ekaterina | Done | bar: 6
User Story 5 | 3 |  |  | 3
Create a back method to return to previous page |  | Ekaterina, Claudia, Joseph | Done | bar: 4
Create a exit method |  | Ekatrina | Done |  | 4: 1.5
User Story 6 | 1 |  |  | 1
Add a password requirement for students |  | Loic | Done | bar: 4
Non-funtional Tasks
Requirement 7 | 0 |  |  | 2
Start having unit tests |  | Emerald, Phuong-Thao | In progress | bar: 5; 9
Requirement 8 | 2 |  |  | 2
Create a flow between levels |  | Everyone | Done |  | 1: 2
Total | 14 |  |  | 12.5 | 2 | 3 | 0.5 | 3.5 | 1 | 1 | 0 | 0.5 | 1 | 0
Remaining Time |  |  |  |  | 10.5 | 7.5 | 7 | 3.5 | 2.5 | 1.5 | 1.5 | 1 | 0 | 0
Points Total (day) |  |  |  |  | 2 | 4 | 2 | 4 |  |  |  | 2 | 2
Points remaining |  |  |  |  | 14 | 10 | 8 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Ideal burndown (day) |  |  |  | 1.4 | 1.4 | 2.8 | 4.2 | 5.6 | 7 | 8.4 | 9.8 | 11.2 | 12.6 | 14
Ideal burndown remaining |  |  |  |  | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4 | 0