## Project
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
User Story 1 | 5
Set up environment |  | Darrin | Done | 1 | 1: 0.75; 2: 0.5
Create Character |  | Darrin | Done | 0.5 | 1: 0; 2: 0.5
Allow it to move |  | Darrin | Done | 1 | 1: 0; 2: 1
User Story 2 | 3
Create code window |  | Ekaterina | Done | 0.5
Create animation window |  | Ekaterina | Done | 0.5
Create base page for animation and code window |  | Ekaterina | Done | 1
User Story 3 | 1
Landing page |  | Joseph | Done | 0.5 | 1: 0.5
Main menu |  | Joseph | Done | 1 | 2: 0.5
User Story 4 | 5
Create drag and drop method |  | Ekaterina | In Progress | 3 | 4: 2; 5: 1
User Story 5 | 1
Save page |  | Claudia and Loic | Done | 0.5 | 3: 0.5; 4: 0.5
Save method |  | Claudia | Done | 2 | 5: 0.75; 6: 0.75
User Story 6 | 3
Access/Load method |  | Claudia and Loic | In progress | 1 | 7: 0.5
User Story 7 | 5
Set up Travis |  | Emerald and Phuong-Thao | In progress | 15 | 2: 1; 3: 2.5; 5: 1; 8: 2; 9: 4
User Story 8 | 2
If Method |  |  |  | 1
User Story 9 | 2
Loop method |  |  |  | 1
User Story 10 | 0.5
Level Menu |  |  |  | 1
User Story 11 | 2
Jump method |  |  |  | 1
User Story 12 | 2
Attack/Break method |  |  |  | 1
User Story 13 | 5
View Progress Report |  |  |  | 5
Non-funtional Tasks
Scrum Tools | 3 | Emerald and Phuong-Thao | Done | 3 | bar: 1 to 2; 6
Total | 36.5 | 0 | 0 | 40.5 | 1: 1.25; 2: 3.5; 3: 3; 4: 2.5; 5: 2.75; 6: 0.75; 7: 0.5; 8: 2; 9: 4; 10: 0
Remaining |  |  |  | 40.5 | 1: 39.25; 2: 35.75; 3: 32.75; 4: 30.25; 5: 27.5; 6: 26.75; 7: 26.25; 8: 24.25; 9: 20.25; 10: 20.25

## Sprint 2
User Stories | Story Points | Responsible | Status | Original estimates | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
User Story 1 | 5
Set up environment |  | Darrin | Done | 1 | 1: 0.75; 2: 0.5
Create Character |  | Darrin | Done | 0.5 | 1: 0; 2: 0.5
Allow it to move |  | Darrin | Done | 1 | 1: 0; 2: 1
User Story 2 | 3
Create code window |  | Ekaterina | Done | 0.5
Create animation window |  | Ekaterina | Done | 0.5
Create base page for animation and code window |  | Ekaterina | Done | 1
User Story 3 | 1
Landing page |  | Joseph | Done | 0.5 | 1: 0.5
Main menu |  | Joseph | Done | 1 | 2: 0.5
User Story 4 | 5
Create drag and drop method |  | Ekaterina | In Progress | 3 | 4: 2; 5: 1
User Story 5 | 1
Save page |  | Claudia and Loic | Done | 0.5 | 3: 0.5; 4: 0.5
Save method |  | Claudia | Done | 2 | 5: 0.75; 6: 0.75
User Story 6 | 3
Access/Load method |  | Claudia and Loic | In progress | 1 | 7: 0.5
User Story 7 | 5
Set up Travis |  | Emerald and Phuong-Thao | In progress | 10 | 2: 1; 3: 2.5; 5: 1; 8: 2; 9: 4
Non-funtional Tasks
Scrum Tools | 3 | Emerald and Phuong-Thao | Done | 3 | bar: 1 to 2; 6
Total | 26 |  |  | 25.5 | 2.25 | 4.5 | 3 | 2.5 | 2.75 | 1.75 | 0.5 | 2 | 4 | 0
Remaining |  |  |  | 25.5 | 23.25 | 18.75 | 15.75 | 13.25 | 10.5 | 8.75 | 8.25 | 6.25 | 2.25 | 2.25